## Sheet1
Risk | Likelihood of Cause (1-5) | Consequence | Risk Rating (low-high) | Action to Take
Running Python main.py on Anaconda Prompt and this causes errors as it requires download of libraries | 5 | The command will not work as we have to install the libraries required | High | Download the libraries or check the files to see if the libraries are showing in DIR, if not then download the libraries
Data Loss | 4 | Loss of data, increase cost | High | Store data in the cloud or somewhere where its less likely to be lost
Incompatible Libraries | 3 | Using Outdated or incompatible libraries, code failure | Medium | Check for updates and check compatibility with pc to see if it is compatible for download
Unavailable Resources | 1 | Project Delays, Increase Cost, Reduced Quality | Low | Alternative Plans
Security Breaches | 2 | Data Loss, App Failure, | Medium | Use Trusted Packages and Security Protocols
Data Integrity | 1 | Data Loss, Misinterpretation | Low | Ensure data validation and verification. Use a liable data storage
Performance | 3 | Slow execution time | Medium | Optimise code and hardware resources, perform load testing before exection
User Error | 3 | Data Loss, Errors | Medium | Provide training and documentation, implement user errorprevention measures
Updates | 3 | Compatability issues, Security Breaches | Medium | Develop and Update strategy, Test updates in a separate environment before development, maintain a role back plan
Hardware Failure | 2 | Data loss, Time | Low | Use both cloud and physical storage as a backup incase of a failure
Data Quality | 3 | Biases, model performance | Medium | Source dataset responsibly, explore numerous datasets and consider the overall quality